## Example - Timeline
Timeline
Partner/WPs | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Work Package 1 Management and coordination | M1: K; M12: PM; M24: PM; M36: FM | K: Kick-off
Task 1.1 Monitoring implementation | [36 empty] | PM: Progress meeting
Task 1.2 Financial, admin and technical coord | [36 empty] | FM: Final meeting
Task 1.3 Quality assurance
Task 1.4 IPR Management | [36 empty] | D: Deliverables - put as in DoW
Task 1.5 Gender strategy | [36 empty] | ID: If internal version of the deliverable is to be reviewed
Work Package 2 | bar: M1 to M18
Task 2.1 | M4: D2.1
Task 2.2 | M6: D2.2
Task 2.3 | bar: M3 to M6
Task 2.4 | bar: M3 to M6
Task 2.5 | M17: ID; M18: D2.3
Work Package 3
Task 3.1 | bar: M1 to M12
Task 3.2 | bar: M12 to M24
Task 3.3 | bar: M18 to M30
Task 3.4 | bar: M18 to M30
Task 3.5
Work Package 4
Task 4.1
Task 4.2
Task 4.3 | bar: M1 to M24
Task 4.4 | bar: M12 to M36
Task 4.5 | bar: M18 to M36
Work Package 5 | bar: M12 to M36
Task 5.1 | bar: M12 to M18
Task 5.2 | bar: M12 to M36
Work Package 6 | bar: M6 to M30
Task 6.1 | bar: M6 to M30
Task 6.2 | bar: M6 to M13
Task 6.3 | bar: M8 to M13; M17 to M18; M23 to M24; M28 to M30
Task 6.4 | bar: M13 to M30
Work Package 7 | bar: M6 to M36
Task 7.1 | bar: M6 to M26
Task 7.2 | bar: M6 to M36
Work Package 8
Task 8.1 | bar: M1 to M6
Task 8.2
Task 8.3
Task 8.4 | bar: M6 to M36
Task 8.5 | bar: M12 to M24
Task 8.6 | bar: M6 to M36

## Example - Task monitoring
Example - Quarterly task monitoring
Partner/WPs | Responsible partner | Responsible person
Work Package 1 Management and coordination |  |  | M3 | M6 | M9 | M12 | M15 | M18 | M21 | M24 | M27 | M30 | M33 | M36
Task 1.1 Monitoring implementation | Coordinator | Jane Smith | Project toolbox ready D1.1 submitted: 10% | Internal reporting complete: 20% | Internal reporting complete: 30% | Yearly monitoring done 35% | Internal reporting complete: 40% | Internal reporting complete: 50% | Internal reporting complete: 60% | Yearly monitoring done, deliverables reviwed: 65% | etc.
Task 1.2 Financial, admin and technical coord | Coordinator | Paul White | M3: System set up, guides available, first reports ok 10%; M6: Internal WP meetings organised, second reports received 15%; M9: Financial data incomplete, chek at the progress meeting 20%; M12: Progress meeting Ok 33%; M15: Two reports missing, P3 and P7 35%; M18: Internal WP meetings organised, EC report submitted: 50%; M21: etc.
Task 1.3 Quality assurance | Coordinator | Paul White | M3: Quality process ok; Deliverables reviewed: 5%; M6: Quality process ok; Deliverables reviewed: 10%; M9: Quality process ok; Deliverables reviewed: 15%; M12: Quality process ok; Deliverables reviewed: 30%; M15: one deliverable rejected internally - WP4! 32%; M18: Quality process ok; Deliverables reviewed: 45%; M21: etc.
Task 1.4 IPR Management | Coordinator | Paul White | M6: IPR plan available, D1.2 submitted 15%; M12: IPR discussed at the progress meeting 33%; M21: etc.
Task 1.5 Gender strategy | Coordinator | Jane Smith | M3: gender action plan done D1.3 submitted: 50%; M12: GAP check done: 60%; M24: GAP check done: 80%; M27: etc.
Work Package 2
Task 2.1 | Partner 3 | John Edwards | M3: Task started, data collection ongoing 80%; M6: D2.1 submitted, task completed 100%
Task 2.2 |  |  | M3: Survey started, data collection ongoing 50%; M6: D2.2 submitted, task completed
Task 2.3 |  |  | M3: Analysis ongoing, slow process, 35%; M6: Analysis delayed, no major impact.; M9: Analysis completed
Task 2.4 |  |  | M3: Stakeholder reaction postitive 40%; M6: Policy-maker reaction slow - no committments reached 45%; M9: Task ended: Delayed results and less signed committment letters than expected - impact on task 2.5
Task 2.5 |  |  | M9: Task started with delay 20%; M12: Methodology concept ready 30%; M15: Work in good progress 55%; M18: ID revised, accepted, D2.3 submitted 100%
Work Package 3
Task 3.1
Task 3.2
Task 3.3
Task 3.4
Task 3.5
Work Package 4
Task 4.1
Task 4.2
Task 4.3
Task 4.4
Task 4.5
Work Package 5
Task 5.1
Task 5.2
Work Package 6
Task 6.1
Task 6.2
Task 6.3
Task 6.4
Work Package 7
Task 7.1
Task 7.2
Work Package 8
Task 8.1
Task 8.2
Task 8.3
Task 8.4
Task 8.5
Task 8.6