## Risk register - V1
Risk Register Template |  | Example:
Risk ID: | Name/identifier for the Risk | Design vs Business (Tecnhical01)
Description: | Describe the risk, the issue it is linked to | Conceptual Design not well aligned with business requirements and domain knowledge
Type of risk: | Technical, Management, Political, etc. | Technical
Impact: | High, Low, Medium | Moderate
Probability: | of the Risk occurring in percentage terms. 100% then the Risk has manifested already and you need to be doing something about it! The other thing here is not to be too optimistic of the Risk occurring, we tend to be over optimistic when we think there we have a degree of control over the Risk. For example people give themselves shorter than required deadlines. Believing that the project or person will be able to deliver. Also we tend to be over-cautious on statistically low Risks occurring due to a phenomenon called the Availability Heuristic. And sometimes the actual probability of the Risk occurring is very low. | 15%
Proximity: | when will this Risk happen. Not all Risks are about the here and now, some may be further off in the future. Thus you can hold off any actions on them. For example “John Smith goes on a 2 month holiday and no work may be done in his work package” if John is going on holiday in a years time then the proximity is far away and you have time to define a response . | M9 …
Cost if risk occurs: | Some Risks may carry a known cost if they occur. For example new hardware may be need to support software testing. This hardware may have a cost already known. | Cost of the Extra time - two weeks approx.
Delay if risk occurs: | And you may already have time delay known if a Risk occurs in days. For example. Results may be delayed by 2 months if John goes on holiday. | Extra time
Counter measures: | What will you do about the Risk? At this point there are only a set number of responses to a Risk these are: | The work plan is structured in two iterative cycles with a synchronization every 6 months to ensure alignment with requirements;
Prevention: You terminate the by doing things differently. For example John Smith going on holiday, cancel his holiday!
Reduction: You reduce the impact of the Risk. John Smith recruits a side kick to learn and take over 1 month before the holiday. Work will still get done but maybe not to the same standard./
Transference: You transfer the risk to another party. This is a special kind of Risk response and normally not seen, An example would be insurance. With insurance you are transferring the Risk impact to someone else.
Acceptance: Sometimes you just have to accept the Risk and if it happens then there is little you can do about it.
Contingency: These are pre planned actions that start when the Risk manifests. For example in EU project this could be Partner X fails to sign the grant agreement. You already have Partner Y set up with the documents ready to take their place.
Risk owner: | The idea of having a Risk owner is that sometimes the person that is best placed to monitor the Risk isn’t the coordinator. The Risk may be an internal issue in a partner’s company. If this Risk occurs then the project partner is the best owner to monitor the Risk and report back to the coordinator. | P4
Author |  | Mr Smith
Date raised |  | -
Date of last Update |  | -
Current status | Open/Closed | -
Actions | Pending/Closed | -

## Risk Register V2
| Risk Description |  | Probability | Impact | Prevention and Mitigation
Technical Risks
example | 1 | Conceptual Design not well aligned with business requirements and domain knowledge | 15% | Moderate | The work plan is structured in two iterative cycles with a synchronization every 6 months to ensure alignment with requirements;
2
3
4
5
6
Financial/Management Risks
example | 7 | Personnel leaves before project completion | 80% | Moderate | Introduction of common responsibility and backup developers (at least two people are familiar with critical aspects within the project)
8
…